## 電動桌
Item | due date | Finished date | Status | Comments
1. Driver+Hall sensor test | 2018-11-02 |  |  | 1.測試兩馬達同上同下 2. 壓力不平衡測試
2. Driver board UART test | 2018-11-09 |  |  | 1.Control motor by UI board
3. Display + Keypad board(UI) | 2018-10-29 |  | 100% | 1. EEPROM R/W 2. 7-segment LED display 3. KeyPad 4. UART interface